## Sheet2
Date | To-do (ML-fbref only pipeline while working on CV feature extraction) | Complete?
June W4 | Project formulation
July W1 | Data Sources research
July W2
July W3
July W4 | Research and practice deployment options
Aug W1 | Exams - so slight write up of project plan and pipeline
Aug W2
Aug W3
Aug W4
Sept W1 | Fbref Data Retrieval and cleaning up
Sept W2
Sept W3 | Setting up Roboflow model to extract object positions (Slight feature engineering if time e.g. distance between detected objects)
Sept W4 | Commit data retrieved + Begin Fbref only model training
Oct W1 | Best ML model selected + Match streams for training CV model found
Oct W2 | Deployment of ML model
Oct W3 | Video feature extraction complete + commit